## Sheet1
Starting Criteria
Week | 7 | Days
Weekly Work | 5 | Days
Weekly Work | 37 | Hours
Prof Dev Module | 0.25 | Proportion of total year effort
Live Project | 0.55 | Proportion of Prof Dev
Effort |  |  |  | Totals |  |  | For Selection |  | For Selection |  | For Selection
Minimum |  |  |  | 5.0875 | Hours per Week |  | Minimum |  | Term |  | Requirements
Expected | 1 | Extra-curricular hours per night |  | 10.0875 | Hours per Week |  | Expected |  | Non-term |  | Design
Stretch | 2 | Extra curricular hours per night |  | 15.0875 | Hours per Week |  | Stretch |  |  |  | Impl
None
|  | Year | Month | Day
Start Date |  | 2018 | 10 | 29 | 2018-10-29
|  |  | Investigation | [6 empty] | 272.625
|  |  | Requirements |  |  | 90.875 | Design |  |  | 181.75 | Implementation | [8 empty] | 424.375 | Release |  |  | 141.3125
Team | MMU POS
|  |  | Term | Term | Term | Term | Term | Term | Term | Term | Non-term | Non-term | Non-term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term |  | Hours
| Member | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
|  | Sprint | 1: 0.75; 3: 1.75; 5: 2.75; 7: 3.75; 9: 4.75; 11: 5.75; 13: 6.75; 15: 7.75; 17: 8.75; 19: 9.75; 21: 10.75
|  | Commencing | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 |  | Minimum | Expected | Stretch | Total
| Anonymous Programmer | Project Manager | None | None | Expected | Expected | Expected | Expected | Expected | Expected | Minimum | Minimum | Minimum | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | None |  | 15.2625 | 161.4 | 0 | 176.6625
| John Doe | Tech Lead | None | None | Expected | Expected | Expected | Expected | Expected | Expected | Minimum | Minimum | Expected | Expected | Expected | Expected | Expected | Expected | Stretch | Stretch | Expected | Expected | Stretch | None |  | 10.175 | 141.225 | 45.2625 | 196.6625
| Oliver Queen | Client Advocate | None | None | Expected | Expected | Expected | Expected | Expected | Expected | Minimum | Minimum | Minimum | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | None |  | 15.2625 | 161.4 | 0 | 176.6625
| Mandem Cedric | Floater | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Expected | Expected | Expected | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | None |  | 81.4 | 30.2625 | 0 | 111.6625
| Barry Allen | User Advocate | None | None | Expected | Expected | Expected | Expected | Expected | Expected | Minimum | Minimum | Minimum | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | None |  | 15.2625 | 161.4 | 0 | 176.6625
| Hours | Minimum | 0 | 0 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 20.35 | 20.35 | 15.2625 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 0
|  | Expected | 0 | 0 | 40.35 | 40.35 | 40.35 | 40.35 | 40.35 | 40.35 | 10.0875 | 10.0875 | 20.175 | 40.35 | 40.35 | 40.35 | 40.35 | 40.35 | 30.2625 | 30.2625 | 40.35 | 40.35 | 30.2625 | 0 | Totals | 137.3625 | 655.6875 | 45.2625 | 838.3125 | Hours
|  | Stretch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.0875 | 15.0875 | 0 | 0 | 15.0875 | 0
| Total Hours | Week | 0 | 0 | 45.4375 | 45.4375 | 45.4375 | 45.4375 | 45.4375 | 45.4375 | 30.4375 | 30.4375 | 35.4375 | 45.4375 | 45.4375 | 45.4375 | 45.4375 | 45.4375 | 50.4375 | 50.4375 | 45.4375 | 45.4375 | 50.4375 | 0 | Total |  |  | 838.3125 |  | Hours
| Total Hours | Sprint | 2018-11-05: 0; 2018-11-19: 90.875; 2018-12-03: 90.875; 2018-12-17: 90.875; 2018-12-31: 60.875; 2019-01-14: 80.875; 2019-01-28: 90.875; 2019-02-11: 90.875; 2019-02-25: 100.875; 2019-03-11: 90.875; 2019-03-25: 50.4375 | Total |  |  | 838.3125 |  | Hours
You have | 838.3125 | Hours, to spend on your project